## L-03
P O V - Harmonogram | [9 empty] | 4 |  | Název akce:
"Název zakázky" | [11 empty] | Zadavatel: | [127 empty] | IČ:
|  | Dnešní datum: | 2026-07-29 |  |  | Wednesday | [5 empty] | Zastoupení zadavatele: | [127 empty] | IČ:
Chládek a Tintěra a.s. Litoměřice
"Název společnosti" | [11 empty] | Projektant | [127 empty] | IČ:
|  | 2016-06-07 |  | úterý | [7 empty] | Autorský dozor projektanta
[42] | [8 empty] | First Day of Week (Mon=2): | 2 | 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08 | 2016-07-09 | 2016-07-10 | 2016-07-11 | 2016-07-12 | 2016-07-13 | 2016-07-14 | 2016-07-15 | 2016-07-16 | 2016-07-17 | 2016-07-18 | 2016-07-19 | 2016-07-20 | 2016-07-21 | 2016-07-22 | 2016-07-23 | 2016-07-24 | 2016-07-25 | 2016-07-26 | 2016-07-27 | 2016-07-28 | 2016-07-29 | 2016-07-30 | 2016-07-31 | 2016-08-01 | 2016-08-02 | 2016-08-03 | 2016-08-04 | 2016-08-05 | 2016-08-06 | 2016-08-07 | 2016-08-08 | 2016-08-09 | 2016-08-10 | 2016-08-11 | 2016-08-12 | 2016-08-13 | 2016-08-14 | 2016-08-15 | 2016-08-16 | 2016-08-17 | 2016-08-18 | 2016-08-19 | 2016-08-20 | 2016-08-21 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-27 | 2016-08-28 | 2016-08-29 | 2016-08-30 | 2016-08-31 | 2016-09-01 | 2016-09-02 | 2016-09-03 | 2016-09-04 | 2016-09-05 | 2016-09-06 | 2016-09-07 | 2016-09-08 | 2016-09-09 | 2016-09-10 | 2016-09-11 | 2016-09-12 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-16 | 2016-09-17 | 2016-09-18 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 | 2016-09-23 | 2016-09-24 | 2016-09-25 | 2016-09-26 | 2016-09-27 | 2016-09-28 | 2016-09-29 | 2016-09-30 | 2016-10-01 | 2016-10-02 | 2016-10-03 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-07 | 2016-10-08 | 2016-10-09 | 2016-10-10 | 2016-10-11 | 2016-10-12 | 2016-10-13 | 2016-10-14 | 2016-10-15 | 2016-10-16 | 2016-10-17 | 2016-10-18 | 2016-10-19 | 2016-10-20 | 2016-10-21 | 2016-10-22 | 2016-10-23 | 2016-10-24 | 2016-10-25 | 2016-10-26 | 2016-10-27 | 2016-10-28 | 2016-10-29 | 2016-10-30 | 2016-10-31 | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-05 | 2016-11-06 | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11 | 2016-11-12 | 2016-11-13 | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-19 | 2016-11-20 | 2016-11-21 | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25 | 2016-11-26 | 2016-11-27 | 2016-11-28 | 2016-11-29 | 2016-11-30 | 2016-12-01 | 2016-12-02 | 2016-12-03 | 2016-12-04 | 2016-12-05 | 2016-12-06 | 2016-12-07 | 2016-12-08 | 2016-12-09 | 2016-12-10 | 2016-12-11 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 | 2016-12-17 | 2016-12-18 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-22 | 2016-12-23 | 2016-12-24 | #REF!
WBS | Název úkolu | provádí | zahájení | dokončení | doba trvání | % Dokončení | Working Days | Days Complete | Days Remaining | SO | 2016-07-04 | [6 empty] | 2016-07-11 | [6 empty] | 2016-07-18 | [6 empty] | 2016-07-25 | [6 empty] | 2016-08-01 | [6 empty] | 2016-08-08 | [6 empty] | 2016-08-15 | [6 empty] | 2016-08-22 | [6 empty] | 2016-08-29 | [6 empty] | 2016-09-05 | [6 empty] | 2016-09-12 | [6 empty] | 2016-09-19 | [6 empty] | 2016-09-26 | [6 empty] | 2016-10-03 | [6 empty] | 2016-10-10 | [6 empty] | 2016-10-17 | [6 empty] | 2016-10-24 | [6 empty] | 2016-10-31 | [6 empty] | 2016-11-07 | [6 empty] | 2016-11-14 | [6 empty] | 2016-11-21 | [6 empty] | 2016-11-28 | [6 empty] | 2016-12-05 | [6 empty] | 2016-12-12 | [6 empty] | 2016-12-19 | [6 empty] | Základní seznam předpisů | Požadované doklady
1 | "Název zakázky" |  |  |  |  | #DIV/0! | 0 | #DIV/0! | #DIV/0!
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
0%
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
0%
0%
[6 empty] | 0% | 0 | 0 | 0
0%
0%
0%
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0
Finanční plnění | [5 empty] | Celkem | [32 empty] | s r p e n | [30 empty] | z á ř í | [29 empty] | ř í j e n | [30 empty] | l i s t o p a d
[26 empty] | 0 |  |  |  |  | 0
Subdodavatelské nasazení | [10 empty] | zpracoval : | [112 empty] | dne :
podpis :
razítko koordinátora :
Termín zahájení stavby (realizace) : | [10 empty] | razítko organizace :
Termín dokončení stavby (realizace) :
Termín předání DSPS :
Doba realizace stavby :
Note on A9: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS is automatically entered, but the formulas are different for different levels.
Note on D9: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on E9: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on F9: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. The duration is from the beginning of the Start date to the ending of the End Date. When the duration is calculated, it is calculated as End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day.
Note on G1: Terms of Use and Copyright: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on G9: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on G38: Terms of Use and Copyright: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on G40: Terms of Use and Copyright: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on H9: Working Days Counts the number of working days using the NETWORKDAYS() formula, which excludes weekends. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached.
Note on I9: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on J9: Calendar Days Remaining This column is calculated by subtracting the Days Complete from the Duration.